# BridgeWork — Delivery Timeline & Completion Goals

Project: BridgeWork (Home Services Platform)
Prepared: February 13, 2026
Last Revised: February 22, 2026
Developer: EDC Development Team
Client: Syed

────────────────────────────────────────────────────────────

## 1. Current Build Status — What's Done

### Overall Progress: ~85% of Full Product

| Area | Status | Completion |
| --- | --- | --- |
| Frontend UI/UX (28 pages) | ✅ Complete | 100% |
| Backend API (8 modules) | ✅ Complete | 100% |
| Authentication (Supabase) | ✅ Complete | 100% |
| Database Schema (15 tables) | ✅ Complete | 100% |
| Real-time Messaging + Image Upload | ✅ Complete | 100% |
| Booking Flow (create, view, status) | ✅ Complete | 100% |
| Pro Registration & Job Acceptance | ✅ Complete | 100% |
| Payment Processing (Stripe Checkout) | ✅ Complete | 100% |
| Stripe Connect (Pro Payouts & Revenue Split) | ✅ Complete | 100% |
| Transaction History | ✅ Complete | 100% |
| Admin Revenue Dashboard | ✅ Complete | 100% |
| Refund Handling | ✅ Complete | 100% |
| Push Notifications | 🔲 Not Started | 0% |
| Email Notifications (Signup Confirm + Password Reset) | ✅ Complete | 100% |
| Review & Rating System (UI wired, backend ready) | 🟡 Partial | 60% |
| Production Deployment (Netlify + Render + Supabase) | ✅ Complete | 100% |

────────────────────────────────────────────────────────────

## 2. What's Left to Build — Remaining Functionalities

### Phase 2A: Payment & Transactions (HIGH PRIORITY) ✅ COMPLETE

| # | Feature | Description | Est. Days | Status |
| --- | --- | --- | --- | --- |
| 1 | Stripe Integration | Connect Stripe API, test keys configured | 2 | ✅ Done |
| 2 | Payment Intent Flow | Create payment intent on booking, checkout page | 1 | ✅ Done |
| 3 | Checkout UI | Stripe Elements card form, order summary, trust badges | 1 | ✅ Done |
| 4 | Payment Success Page | Post-payment confirmation with booking details | 0.5 | ✅ Done |
| 5 | Transaction History | User transaction history page with pagination | 1 | ✅ Done |
| 6 | Promo Code Redemption | Apply promo codes at checkout (end-to-end wired) | 0.5 | ✅ Done |
| 7 | Dashboard Payment Status | Payment badges + Pay Now buttons on booking cards | 0.5 | ✅ Done |
| **Subtotal** |  |  | **6.5 days** | **100%** |

### Phase 2B: Stripe Connect — Pro Payouts & Revenue Split (HIGH PRIORITY) ✅ COMPLETE

| # | Feature | Description | Est. Days | Status |
| --- | --- | --- | --- | --- |
| 1 | Pro Stripe Onboarding | Express account creation + onboarding link in pro dashboard | 2 | ✅ Done |
| 2 | `stripe_account_id` | Already exists on `pro_profiles` table, wired to Connect flow | 0.5 | ✅ Done |
| 3 | Payment Splitting | `application_fee_amount` + `transfer_data` on payment intents | 1 | ✅ Done |
| 4 | Platform Commission Config | Configurable via `PLATFORM_COMMISSION_RATE` env var (default 15%) | 0.5 | ✅ Done |
| 5 | Pro Earnings Dashboard | Real earnings data, Stripe dashboard link, transaction history | 2 | ✅ Done |
| 6 | Admin Revenue Dashboard | Full revenue overview, fee breakdown, refund modal | 2 | ✅ Done |
| 7 | Refund Handling | Admin can process Stripe refunds, updates booking + notifications | 1.5 | ✅ Done |
| 8 | Testing & QA | End-to-end test with Stripe Connect test accounts | 1 | 🔲 Pending |
| **Subtotal** |  |  | **10.5 days** | **~95%** |

Revenue Model: 15% platform commission per booking. See docs/Payment_Revenue_Breakdown.md for detailed scenario-based calculations, fee structures, and monthly revenue projections.

### Phase 3: Notifications & Communication (MEDIUM PRIORITY)

| # | Feature | Description | Est. Days |
| --- | --- | --- | --- |
| 1 | Email Notifications | Booking confirmation, status updates, reminders (SendGrid/Resend) | 2 |
| 2 | Push Notifications | Browser push for new messages, job alerts, booking updates | 2 |
| 3 | In-App Notification Center | Bell icon with notification dropdown (DB table exists) | 1 |
| **Subtotal** |  |  | **5 days** |

### Phase 4: Advanced Features (MEDIUM PRIORITY)

| # | Feature | Description | Est. Days |
| --- | --- | --- | --- |
| 1 | Review & Rating UI | Post-job review form, star ratings, pro response | 1 |
| 2 | Pro Availability Calendar | Set weekly schedule, time-off management | 1.5 |
| 3 | Saved Addresses | Manage multiple addresses (DB table exists) | 0.5 |
| 4 | Favorites | Save favorite pros (DB table exists) | 0.5 |
| **Subtotal** |  |  | **3.5 days** |

### Phase 5: Admin & Operations (LOWER PRIORITY)

| # | Feature | Description | Est. Days |
| --- | --- | --- | --- |
| 1 | Admin Dashboard | User management, booking oversight, analytics | 3 |
| 2 | Pro Application Review | Admin approves/rejects pro applications | 1 |
| 3 | Support Ticket System | User submits tickets, admin manages (DB table exists) | 1.5 |
| 4 | Content Management | Service/category CRUD from admin panel | 1 |
| **Subtotal** |  |  | **6.5 days** |

### Phase 6: Polish & Launch Prep (REQUIRED)

| # | Feature | Description | Est. Days |
| --- | --- | --- | --- |
| 1 | Production Deployment | Final deploy to Render + Netlify with env vars | 0.5 |
| 2 | SEO & Meta Tags | Open Graph, Twitter cards, page titles | 0.5 |
| 3 | Error Handling & Loading States | Consistent error boundaries, skeleton loaders | 1 |
| 4 | Mobile Responsiveness Audit | Test all 26 pages on mobile/tablet | 1 |
| 5 | Performance Optimization | Image optimization, lazy loading, bundle size | 1 |
| 6 | Security Audit | Input sanitization, rate limiting, CORS hardening | 1 |
| 7 | Google Maps / Geolocation | Address autocomplete, pro proximity search, map view (nice-to-have) | 2 |
| **Subtotal** |  |  | **7 days** |

────────────────────────────────────────────────────────────

## 3. Delivery Timeline

### Timeline Option A: MVP Launch (Marketing-Ready)

Target: February 27, 2026 (restored to original date per client request)

Focus on what's needed for marketing and early user testing:

| Week | Dates | Deliverables | Status |
| --- | --- | --- | --- |
| **Week 1** | Feb 14–20 | Stripe payment integration, email notifications, production deployment | ✅ Done |
| **Week 2** | Feb 22–27 | Review & rating system, Stripe live testing, QA, MVP launch | � In Progress |

MVP Includes:

• ✅ All 26 pages (done)

• ✅ Auth, booking, messaging (done)

• 🆕 Payment processing (Stripe)

• 🆕 Email notifications (booking confirmations)

• 🆕 Review & rating system

• 🆕 Production deployment (live URL)

MVP Excludes (deferred to post-launch):

• Admin dashboard

• Push notifications

• Pro availability calendar

• Support ticket system

────────────────────────────────────────────────────────────

### Timeline Option B: Full Product Launch

Target: March 13, 2026 (restored to original date)

| Week | Dates | Deliverables | Status |
| --- | --- | --- | --- |
| **Week 1** | Feb 14–20 | Stripe payment + email notifications + production deploy | ✅ Done |
| **Week 2** | Feb 22–27 | Review system, Stripe live testing, QA, **MVP launch** | � In Progress |
| **Week 3** | Feb 28–Mar 6 | Admin dashboard, push notifications, pro availability | 🔲 Pending |
| **Week 4** | Mar 7–13 | Polish, security audit, mobile audit, performance, **full launch** | 🔲 Pending |

Full Product Includes: Everything in MVP + admin panel, push notifications, pro scheduling, support system, full polish.

────────────────────────────────────────────────────────────

### Week 2 Build Plan: Review & Rating System (Feb 22–27)

Current Status: Backend 100% done, Frontend 60% done (UI exists with mock data)

#### What's Already Built

| Component | Layer | Status |
| --- | --- | --- |
| `reviews` DB table (with rating trigger) | Database | ✅ Done |
| `reviewsController.js` — create, getByProId, respondToReview | Backend | ✅ Done |
| `reviews.js` routes — POST, GET, respond | Backend | ✅ Done |
| `reviewsAPI` — create, getByProId, respond | Frontend API | ✅ Done |
| Pro profile page — review display UI | Frontend | 🟡 Mock data |
| DB trigger — auto-updates pro `rating` + `total_reviews` on new review | Database | ✅ Done |

#### What Needs to Be Built

| # | Task | Description | Est. Hours | Target Date |
| --- | --- | --- | --- | --- |
| 1 | **Review Form Component** | Star rating selector, comment textarea, image upload. Shown on completed bookings. | 3h | Feb 22 |
| 2 | **"Leave a Review" trigger** | Add review button/prompt on completed booking cards in user dashboard | 2h | Feb 22 |
| 3 | **Wire Pro Profile to Real API** | Replace mock data in `pro-profile/[id]/page.js` with real `prosAPI` + `reviewsAPI` calls | 3h | Feb 23 |
| 4 | **Pro Response UI** | Add "Respond to Review" form in pro dashboard for each review received | 2h | Feb 23 |
| 5 | **Review display on booking detail** | Show review (if exists) on booking detail page | 1h | Feb 24 |
| 6 | **Stripe Live Mode Testing** | Switch to live Stripe keys, test real payment with real card, verify capture/refund | 3h | Feb 25 |
| 7 | **QA & Bug Fixes** | End-to-end testing of full user journey: signup → book → pay → complete → review | 4h | Feb 26 |
| 8 | **Production Deploy & Verify** | Final deploy to Netlify + Render, smoke test all features | 2h | Feb 27 |

#### Step-by-Step Implementation Plan

Day 1 (Feb 22) — Review Form + Trigger

Create ReviewForm component with: - 5-star interactive rating selector
- Comment textarea (optional)
- Image upload (optional, reuse existing upload logic)
- Submit button → calls `reviewsAPI.create()`

Add "Leave a Review" button on completed booking cards in user dashboard

Create review submission modal/page that opens from the booking card

Test: create a review → verify it appears in DB → verify pro rating auto-updates

Day 2 (Feb 23) — Pro Profile + Pro Response

Replace all mock data in pro-profile/[id]/page.js with real API calls: - Fetch pro profile via `prosAPI.getById(id)`
- Fetch reviews via `reviewsAPI.getByProId(proId)`
- Display real rating distribution, real review list

Add "Respond to Review" form in pro dashboard: - List all reviews for the pro
- Text input for response → calls `reviewsAPI.respond(id, { response })`
- Show existing responses inline

Day 3 (Feb 24) — Polish + Integration

Show review on booking detail page (if review exists for that booking)

Add review count badges on pro cards in search results

Handle edge cases: no reviews yet, loading states, error states

Test full flow: user completes booking → leaves review → pro responds

Day 4 (Feb 25) — Stripe Live Mode

Create Stripe live mode keys (from Stripe dashboard)

Update Render env vars with live STRIPE_SECRET_KEY

Update Netlify env vars with live NEXT_PUBLIC_STRIPE_PUBLISHABLE_KEY

Test real payment with a real credit card ($1 test charge)

Verify: payment captured → pro payout → refund works

Redeploy both frontend and backend

Day 5 (Feb 26) — QA & Bug Fixes

Full end-to-end test of user journey on production: - Sign up → confirm email → log in
- Browse services → book a service
- Pay via Stripe → verify payment success
- Pro accepts job → completes job
- User leaves review → pro responds

Fix any bugs found during testing

Mobile responsiveness check on key pages

Day 6 (Feb 27) — MVP Launch

Final production deploy

Smoke test all critical paths

Share live URL with client

MVP officially launched 🚀

────────────────────────────────────────────────────────────

## 4. Recommended Path for Marketing

For marketing preparation, I recommend Timeline Option A (MVP Launch by Feb 27). This gives you:

A live, working URL to share with potential users and investors

Core user journey complete — browse → book → pay → message → review

Professional appearance — all 26 pages with consistent branding

Real functionality — not a prototype, actual working features

### What Marketing Can Start Preparing Now:

• Screenshots of all major pages (homepage, services, dashboard, messaging)

• Demo video (script provided separately)

• Feature list for marketing materials

• Live URL will be available after deployment (within 1–2 days)

────────────────────────────────────────────────────────────

## 5. Additional Notes & Things to Be Aware Of

### Technical Considerations

Supabase Free Tier Limits — Currently on free tier. For production with real users, upgrade to Pro plan ($25/mo) for: - 8GB database storage (vs 500MB free)
- 250GB bandwidth (vs 2GB free)
- 100GB file storage (vs 1GB free)
- No pausing after 1 week of inactivity

Render Free Tier — Backend on free tier spins down after 15 min of inactivity. First request after sleep takes ~30 seconds. For production: - Upgrade to Starter plan ($7/mo) for always-on
- Or use a health check ping service

Stripe Setup Required — Free to create, pay-per-transaction only. Need a Stripe account with: - API keys (publishable + secret)
- Stripe Connect setup for pro payouts
- Webhook endpoint configured
- Test mode for development (free, fake cards), live mode for production
- Stripe Fees:
  - Per transaction: 2.9% + $0.30 CAD per successful charge
  - Stripe Connect (pro payouts): additional 0.25% + $0.25 per payout
  - Disputes/chargebacks: $15 CAD per dispute (rare, <1% of transactions)
- What is a chargeback? When a customer contacts their bank to reverse a payment (e.g., "I didn't authorize this" or "service not received"). The bank pulls the money back and Stripe charges a $15 fee regardless of outcome.
- Example transaction breakdown:
  - Customer pays $100 → Stripe takes $3.20 → Platform receives $96.80
  - Platform takes 15% commission ($15) → Pro receives $85 minus Connect fee ($0.46) = $84.54
  - Platform net profit: ~$15 per $100 job (commission % is configurable)

Domain Name — Currently using Netlify subdomain (e.g., bridgework-app.netlify.app). A custom domain is essential for branding and credibility. - Purchase from a domain registrar, then point DNS to your hosting provider
- SSL certificate is automatic on all hosting providers listed below
- Recommended domains for BridgeWork:
  | Domain | Est. Price | Notes |
  |--------|-----------|-------|
  | `bridgework.ca` | ~$12–15/yr | Best for Canadian market |
  | `bridgework.com` | ~$10–12/yr | Best for global reach (check availability) |
  | `bridgeworkservices.com` | ~$10–12/yr | Fallback if `.com` is taken |
  | `getbridgework.com` | ~$10–12/yr | Marketing-friendly alternative |
- Domain registrar pricing (annual):
  | Registrar | `.com` | `.ca` | `.io` |
  |-----------|--------|-------|-------|
  | Namecheap (recommended) | ~$10/yr | ~$12/yr | ~$30/yr |
  | Cloudflare Registrar | ~$10/yr | N/A | ~$28/yr |
  | GoDaddy | ~$12/yr | ~$15/yr | ~$35/yr |
- Recommendation: Namecheap or Cloudflare — cheapest at-cost pricing, no upsells

Hosting Options — Current setup and alternatives: 
 Current Setup (What We Use Now): | Component | Provider | Tier | Cost |
|-----------|----------|------|------|
| Frontend | Netlify | Free | $0 (100GB bandwidth, auto-deploy from Git) |
| Backend API | Render | Free | $0 (spins down after 15 min inactivity) |
| Database | Supabase | Free | $0 (500MB DB, 1GB storage) |
 Why Netlify + Render + Supabase? - Zero cost to start — no upfront investment
- Auto-deploy on every Git push
- SSL included on all providers
- Scales easily by upgrading tiers 
 Alternative Hosting Options: | Option | Frontend | Backend | Database | Monthly Cost | Pros | Cons |
|--------|----------|---------|----------|-------------|------|------|
| A: Current (Netlify + Render + Supabase) | Netlify Free | Render Free | Supabase Free | $0 | Zero cost, easy setup | Render cold starts (30s), Supabase limits |
| B: Current (Paid tiers) | Netlify Pro $19 | Render Starter $7 | Supabase Pro $25 | $51/mo | Always-on, production-ready | Monthly cost |
| C: Vercel + Railway | Vercel Free | Railway $5 | Supabase Pro $25 | $30/mo | Fast deploys, no cold starts | Railway limited free tier |
| D: VPS (DigitalOcean) | DO Droplet | Same droplet | Supabase Pro $25 | $31–37/mo | Full control, no cold starts | Requires server management |
| E: AWS (Amplify + EC2) | Amplify Free | EC2 t3.micro | RDS/Supabase | $15–50/mo | Enterprise-grade | Complex setup, AWS learning curve |
 Recommendation: Stay with Option A (free tiers) for MVP launch. Upgrade to Option B (paid tiers, ~$51/mo) when real users start using the platform. This avoids Render cold starts and Supabase limits.

Email Service — Need an email provider for transactional emails: - Required for: booking confirmations, password resets, pro notifications
- Email provider pricing:
  | Provider | Free Tier | Paid |
  |----------|-----------|------|
  | Resend (recommended) | 3,000 emails/month | $20/mo for 50K |
  | SendGrid | 100 emails/day (~3,000/mo) | $15/mo for 50K |
  | AWS SES | 3,000/mo free (if on EC2) | $0.10 per 1,000 |
- Recommendation: Start with Resend — free tier is sufficient for early launch, no credit card required

### Business Considerations

Terms of Service & Privacy Policy — Pages exist with placeholder content. Need legal review before launch with real users.

Insurance Page — Currently shows placeholder providers (belairdirect, Intact). Need actual partnership details or remove before launch.

Pro Verification — Current flow creates pro accounts but doesn't include actual background check integration. This is a manual process for now.

Pricing — Service prices are seeded with sample data. Need real pricing from the business team before launch.

Geographic Scope — The platform references Canadian addresses (Ontario). Confirm the initial launch market.

### Security Notes

Rate Limiting — Not yet implemented on API endpoints. Should add before production launch to prevent abuse.

Input Validation — Basic validation exists. Need comprehensive sanitization audit before handling real user data.

File Upload — Image uploads limited to 5MB, image types only. Storage bucket is public (images accessible via URL). Consider signed URLs for sensitive content.

────────────────────────────────────────────────────────────

## 6. Risk Register

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Supabase free tier limits hit | High | Medium | Upgrade to Pro plan before marketing push |
| Render cold starts (30s delay) | Medium | High | Upgrade to paid plan or add health ping |
| Stripe integration complexity | Medium | Low | Well-documented API, standard flow |
| Mobile responsiveness gaps | Medium | Medium | Dedicated mobile audit in Week 2 |
| Legal compliance (ToS/Privacy) | High | Medium | Get legal review before public launch |

────────────────────────────────────────────────────────────

## 7. Cost Breakdown — Launch Budget

### MVP Launch (Minimum — Free Tiers)

| Service | Cost |
| --- | --- |
| Stripe | **$0** (pay per transaction only) |
| Netlify hosting | **$0** (free tier: 100GB bandwidth) |
| Render backend | **$0** (free tier: spins down after 15 min) |
| Supabase | **$0** (free tier: 500MB DB, 1GB storage) |
| Email — Resend | **$0** (free tier: 3,000 emails/month) |
| Domain name | **~$12/year** |
| **Total to launch MVP** | **~$12 one-time (domain only)** |

### Production-Grade (Paid Tiers — When Real Users Come)

| Service | Cost |
| --- | --- |
| Stripe | 2.9% + $0.30 per transaction |
| Netlify Pro | $19/mo |
| Render Starter | $7/mo |
| Supabase Pro | $25/mo |
| Email — Resend | $0–$20/mo |
| Domain name | ~$12/year |
| **Total monthly (production)** | **~$51–71/month** + transaction fees |

### Stripe Revenue Example

| Monthly Bookings | Avg. Job Price | Gross Revenue | Stripe Fees | Platform Commission (15%) | Net Platform Revenue |
| --- | --- | --- | --- | --- | --- |
| 50 jobs | $100 | $5,000 | ~$160 | $750 | **~$590/mo** |
| 100 jobs | $100 | $10,000 | ~$320 | $1,500 | **~$1,180/mo** |
| 200 jobs | $150 | $30,000 | ~$640 | $4,500 | **~$3,860/mo** |

────────────────────────────────────────────────────────────

## 8. Summary

| Metric | Value |
| --- | --- |
| **Current Completion** | ~85% of full product |
| **Pages Built** | 28+ (incl. transactions, admin revenue, checkout, payment success) |
| **API Modules** | 8 (incl. Stripe Connect controller) |
| **DB Tables** | 15 / 15 |
| **Remaining Work** | ~15 dev days (notifications, reviews, admin panel, polish) |
| **MVP Launch Cost** | ~$12 (domain only) |
| **Production Monthly Cost** | ~$51–71/month + Stripe fees |
| **MVP Target** | **February 27, 2026** |
| **Full Launch Target** | **March 13, 2026** |
| **Critical Blockers** | None — all remaining work is additive |

────────────────────────────────────────────────────────────

Document prepared: February 13, 2026
Last updated: February 22, 2026 (timeline restored to original dates per client, added review system build plan)